3.18.26 GUCC Cross Bore Committee Meeting Minutes

1. Meeting Purpose

- Re‑establish momentum following the recent conference

- Advance the “Call Before You Clear” initiative in Georgia

- Identify public awareness opportunities

- Define subcommittees, research needs, and policy pathways

- Capture outreach, education, and white‑paper initiatives for 2026

## 2. Key Highlights (Executive Summary)

- Major outcome: Agreement to move forward with a Georgia “Call Before You Clear” model, leveraging successful programs in other states.

- Three core workstreams identified:

  - Education & awareness

  - Data / ticketing & notification feasibility

  - Policy and legislative alignment

- Strong external momentum:

  - Requests to speak at GDOT district meetings, UCCs, municipalities, and trade associations.

  - Engagement opportunities with PHCC (Plumbing Heating Cooling Contractors Association) and Georgia 811 Damage Prevention Summits.

- Two new white paper initiatives proposed:

  - Sewer cleaning & jetting damage prevention best practices

  - Cross‑utility emergency response best practices

- Increased emphasis on locatability of sewer laterals, tracer wire, medallions, and marking laws.

## 3. Safety & Values Moment

- Seasonal safety reminder (weather variability, vehicle readiness).

- Reinforced importance of 811 usage and education for homeowners and families.

- Emphasis on inclusive, cross‑industry collaboration as a core value of damage prevention.

## 4. Primary Discussion Topics & Decisions

### A. Call Before You Clear – Georgia Model

Decision: Proceed with development of a Georgia‑specific program proposal.

Defined Subcommittees:

- Best Practices Research

  - Review other states (e.g., Pennsylvania) with formal Call Before You Clear programs.

- Implementation and Adaptation

  - Assess how Georgia 811 could support specialized ticketing or notifications.

  - Estimate volume impacts using utility‑provided data.

- Policy / Legislative Framework

  - Research dig laws and regulatory structures that support these programs.

  - Present findings to GUCC and 811 Boards.

### B. Public Awareness & Outreach

Confirmed and potential engagement opportunities include:

- GDOT – Seven districts (quarterly utility meetings), requested a presentation at at least one meeting per district

- Fayette County UCC – April 23 (already scheduled)

- Municipalities – City of Gainesville, City of Savannah

- Trade Associations:

  - PHCC (Plumbing Heating Cooling Contractors Association)

    - AGL will provide educational materials and possibly staff for the PHCC summit via GA 811 booth.

  - GUCA (Georgia Utility Contractors Association)

  - Georgia Municipal Association (future outreach)

- Georgia 811 Damage Prevention Summits

  - Planned locations: Dalton, Savannah, Braselton (Aug–Oct timeframe)

- Georgia Pipeline Emergency Responders Initiative (GPERI)

  - Lead training for first responders on how to react to a gas emergency.

### C. Education & Training Strategy

- Agreement to create multiple versions of presentations:

  - 10–15 minute “safety moment” version

  - ~20‑minute lunch‑and‑learn version

- Reuse and adapt existing presentations already uploaded to SharePoint.

- Share to GUCC Cross Bore Committee website so committee members have materials available.

### D. Sewer Lateral Locatability & Marking

- Discussion reinforced that legally, under the Dig Law, new underground installations must be locatable.

- Methods discussed:

  - Tracer wire

  - Permanent surface medallions

- Recognized as a root cause issue contributing to cross bores.

### E. White Paper Initiatives (New)

- Sewer Cleaning & Jetting Damage Prevention

  - Focus on preventing large‑diameter sewer and gas incidents.

- Emergency Response Best Practices for Utility Cross Bores

  - Expand existing Southern Company Gas practices into an industry model.

  - Potential submission to CGA (Common Ground Alliance).

## 5. Action Items & Owners

| # | Action Item | Owner(s) |
| --- | --- | --- |
| 1 | Research other states’ Call Before You Clear programs (e.g., PA) | Subcommittee (TBD) |
| 2 | Translate best practices into Georgia 811 operational needs | Subcommittee (TBD) |
| 3 | Gather cross‑bore volume data from utilities | Subcommittee (TBD) |
| 4 | Build mapping/visualization of cross‑bore data | Subcommittee (TBD) |
| 5 | Draft policy / legislative framework proposal | Subcommittee (TBD) |
| 6 | Track and manage public awareness speaking requests | April Johnson + Danny Boswell |
| 7 | Create outreach tracking/reporting tool | April Johnson |
| 8 | Coordinate PHCC engagement and survey distribution | April Johnson + Becky Kinsey |
| 9 | Explore Georgia 811 Summit participation (booth/materials) | Becky Kinsey + Committee |
| 10 | Develop sewer cleaning & jetting white paper | Committee (TBD) |
| 11 | Develop emergency response best‑practice white paper | Committee (TBD) |
| 12 | Reach out to GUCA leadership | Danny Boswell |
| 13 | Follow up with Georgia Pipeline Emergency Responders Initiative (GPERI) outreach | Tiffany Baker + April Johnson |

## 7. Next Steps

- Meeting minutes and recording to be distributed (target mentioned: end of week).

- Formation of subcommittees and breakout sessions between monthly meetings.

- Continued scheduling of outreach and awareness events.

- Development of proposals, white papers, and education materials throughout 2026.